## KD Changes
Building ID | 0041 |  |  |  | Status Date: | 2015-08-07 |  |  | # of Rooms Waiting for eBARS Tags | # of Rooms Waiting for Door Signs |  |  |  | Verified By: | Date:
Name | Anderson Hall Tower |  |  |  | CAD Operator | Adam Davidson |  |  | 6 | 4
Room ID | Floor | Description of Change | Change to SqFt | Old SqFt | New SqFt | eBARS Tag Status | Door Signage | Comments | eBARS Tag Progress | Date | Issues | New Sign Progress | Date | Issues
0100B | 01 | Room Created | Yes | 0 | 40 | New Tag Required | New Sign Required | Vestibule created / no new door | 0
0100C | 01 | Room Made Smaller | Yes | 65 | 59 | No Change | N/A | Wall made thicker. Fixture relocated.
103 | 01 | Room Deleted | Yes | 103 | 0 | Remove Old Tag | Remove Old Sign | Room Number is not used | 0 |  |  | 0
103A | 01 | Room Created | Yes | 0 | 40 | New Tag Required | New Sign Required | Men's RR Created | 0
103B | 01 | Moved a Door | Yes | 28 | 29 | New Tag Required | N/A | RR Deleted, New janitor closet created in space | 0 |  |  | N/A
104 | 01 | Change Door Swing | No |  |  | New Tag Required | N/A | New Fixtures, new Women's RR | 0 |  |  | N/A
109 | 01 | Wall Added | Yes | 327 | 307 | No Change | N/A |  | N/A |  |  | N/A
110 | 01 | Soffit Added | Yes | 279 | 278 | No Change | N/A |  | N/A |  |  | N/A
111 | 01 | Room Made Smaller | Yes | 870 | 255 | N/A | N/A | Divided into 3 rooms. | N/A |  |  | N/A
111B | 01 | Room Created | Yes | 0 | 254 | New Tag Required | New Sign Required | Dean's Suite created from part of 111 | 0
111C | 01 | Room Created | Yes | 0 | 343 | New Tag Required | New Sign Required | Conference Room created from part of 111. Stairs removed. Exterior door was deleted and infilled with new window that match existing.
[6 empty] | Total Tags Required | Total Signs Required |  | Total Tags Installed |  |  | Total Signs Installed
[6 empty] | 6 | 4 |  | 0 |  |  | 0
End of Data Validation

## SAP Changes
Building ID | 0041 |  | Status Date: | 2015-08-07
Name | Pence Hall |  | CAD Operator | Adam Davidson
SAP Functional Location | Room Description | Action | SqFt | Comments
LX-0041-01-100A | PENCE HALL - Room 100A | Add
LX-0041-01-100B | PENCE HALL - Room 100B | Add
LX-0041-01-100C | PENCE HALL - Room 100C | Add
LX-0041-01-103 | PENCE HALL - Room 103 | Inactivate
LX-0041-01-103A | PENCE HALL - Room 103A | Add
LX-0041-01-109A | PENCE HALL - Room 109A | Add
LX-0041-01-111B | PENCE HALL - Room 111B | Add
LX-0041-01-111C | PENCE HALL - Room 111C | Add
LX-0041-01-112A | PENCE HALL - Room 112A | Inactivate
LX-0041-01-113C | PENCE HALL - Room 113C | Add
LX-0041-01-114 | PENCE HALL - Room 114 | Inactivate
LX-0041-01-119 | PENCE HALL - Room 119 | Inactivate
End of Data Validation

## Lookup
No Change | Yes | Adam Davidson | No Change | Add A Door | Requested | Add
New Tag Required | No | Janet Schwartz | New Sign Required | Add This Room Number | Awaiting Installation | Inactivate
N/A | N/A | Barry Richardson | N/A | Change Door Swing | Installed | Change SqFt
Action Required |  | Laura Greenfield | Action Required | Delete This Room Number | Removed | Change Description
Remove Old Tag |  | Chris Curtis | Remove Old Sign | Gross | 0
|  | Gretchen Tucker | Move Sign to New Location | Moved a Wall And Door
|  | Suzanna Bentley |  | New Room Added For SAP Purposes
No Change to Room
Door Removed, Door Opening Exists
Remove A Door
Room Label Change: xxx Changed To xxx
Room Created
Room Deleted
Room Made Bigger
Room Made Smaller
Wall And Doorway Removed Between Rm xxx And Rm xxx
Walls Removed
Windows Added

## BuildingList
Building ID | Building Name
0001 | Taylor Education Building
0002 | Scott Street Building
0003 | Research Facility #1
0004 | Central Heating Plant #2
0005 | Frank D. Peterson Service Building
0006 | Patterson Hall
0007 | Blazer Hall
0008 | Boone Faculty Center
0009 | William B. Sturgill Development Building
0010 | Gatehouse KY Clinic
0011 | Dickey Hall
0012 | Memorial Coliseum
0014 | Engineering Transportation Research Garage
0015 | Old Engineers Residence
0016 | Fine Arts Guignol Building
0017 | Safety & Security
0019 | Lafferty Hall
0020 | White Hall Classroom Building
0021 | Student Center Addition
0022 | Patterson Office Tower
0023 | Barker Hall
0024 | Alumni Gym
0025 | Student Center
0026 | Frazee Hall
0027 | Main Building
0028 | Ezra Gillis Building
0029 | Carol Martin Gatton Business & Economics Building
0030 | Miller Hall
0031 | Gatehouse Gate 2
0032 | 109 State St
0033 | Engineering Annex
0034 | Margaret I. King Library
0035 | Maxwell Place
0036 | Pence Hall
0037 | Grehan Journalism Building
0038 | S. J. Sam Whalen Building
0039 | Kastle Hall
0040 | McVey Hall
0041 | Anderson Hall Tower
0042 | C. W. Mathews Building
0043 | Law Building
0044 | Memorial Hall
0045 | Erikson Hall
0046 | Mineral Industries Building
0047 | Terrell Civil Engineering Building
0048 | Slone Research Building
0049 | Funkhouser Building
0050 | Chemistry-Physics Building
0051 | Breckinridge Hall
0052 | Kinkead Hall
0053 | Bradley Hall
0054 | Bowman Hall
0055 | Tobacco Research Laboratory
0056 | Scovell Hall
0057 | Small Animal Lab
0058 | Agronomy Head House and Greenhouses 1 & 2
0059 | Chi Omega Sorority
0061 | Delta Delta Delta Sorority
0062 | Alpha Delta Pi Sorority
0064 | Thomas Poe Cooper Building
0065 | Shively Track & Field Stadium
0066 | Kelley Hall
0067 | Dimock Animal Pathology
0068 | 653 Maxwelton Ct
0069 | Med Center Annex #5
0070 | Central Hall II
0071 | Central Hall I
0072 | Cooker Trailer Storage
0073 | Multi-Disciplinary Science Building (MDS)
0074 | 453 Columbia
0075 | Gatehouse Roach Bldg
0076 | Medical Center Heating and Cooling Plant
0077 | Medical Behavioral Science Building
0078 | Medical Center Storage Facility
0079 | Agriculture Motor Pool
0080 | Cooling Plant #1
0081 | University Lofts
0082 | Agriculture Science Center North
0083 | Seed House
0084 | Ben F. Roach Cancer Care Facility
0085 | Cooper House
0086 | Champions Court I
0087 | Dorothy Enslow Combs Cancer Research Building
0088 | E. S. Good Barn
0089 | Marylou Whitney and John Hendrickson Cancer Facility for Women
0090 | Gluck Equine Research Building
0091 | Haggin Hall
0092 | Reynolds Warehouse #1
0093 | Reynolds Warehouse #2
0094 | Reynolds Warehouse #3
0095 | Woodland Glen I
0096 | Commonwealth Village #2
0097 | Commonwealth Village #1
0098 | Mining & Minerals Resources Building
0099 | Center for Robotics & Manufacturing Systems
0100 | Wendell & Vickie Bell Soccer Complex
0101 | Maintenance Building (Athletics)
0102 | Shively Sports Center
0103 | Soccer Filming Tower
0104 | Helen King Alumni Building
0105 | Woodland Glen II
0106 | Sigma Nu Fraternity
0107 | Delta Gamma Sorority
0108 | Champions Court II
0109 | Delta Zeta Sorority
0110 | Kappa Alpha Theta Sorority
0111 | Phi Sigma Kappa Fraternity
0113 | Alpha Gamma Delta Sorority
0117 | Kappa Delta Sorority
0118 | Delta Sigma Phi Fraternity
0119 | Alpha Gamma Rho Fraternity
0120 | The 90
0121 | New Farmhouse Fraternity
0122 | Blanding II
0123 | Blanding III
0124 | Blanding Tower
0125 | Blanding IV
0126 | Complex Commons
0127 | Kirwan IV
0128 | Kirwan Tower
0129 | Kirwan III
0130 | Kirwan II
0131 | Kirwan I
0132 | Blanding I
0135 | Head House
0136 | Greenhouse No 2
0137 | Greenhouse No 4
0138 | Greenhouse No 7
0140 | Greenhouse No 5
0141 | Greenhouse No 3
0142 | Greenhouse No 1
0143 | Greenhouse No 9
0144 | Greenhouse No 11
0145 | Greenhouse No 6
0146 | Greenhouse No 12
0147 | 106 Conn Terrace
0148 | Gatehouse Administration Dr
0149 | Gatehouse Rose & Chem/Physics
0150 | Gatehouse Student Center
0151 | Alpha Gamma Rho Fraternity
0152 | Gatehouse Med Plaza
0153 | Academic Science Building
0154 | Gatehouse Med Plaza
0155 | Gatehouse KY Clinic
0156 | Residence Motor Pool
0157 | Gatehouse Young Library
0158 | 113 State St
0159 | Woodland Glen III
0160 | Isolation Barn Incinerator
0161 | Isolation Barn
0162 | Agricultural Machine Research Lab
0163 | Garage by Motor Pool Residence
0164 | Woodland Glen IV
0165 | Bus Shelter #5
0166 | Woodland Glen V
0167 | Shawneetown Bldg A
0170 | Shawneetown Bldg B
0173 | Shawneetown Bldg D
0174 | Shawneetown Bldg F
0175 | Shawneetown Bldg E
0176 | Shawneetown Bldg C
0177 | Stoll Field Viewing Tower
0178 | Parking Garage No 1
0180 | Parking Garage No 2
0182 | Parking Garage No 3
0183 | Wethington Allied Health Building
0184 | Parking Garage No 5
0185 | 1037 S. Limestone
0187 | Cooling Plant #2
0189 | Phi Mu
0190 | Arts Metal Building
0191 | Reynolds Warehouse #4
0192 | Maxwell Place Garage
0193 | Lancaster Aquatics
0194 | Boone Tennis Center
0196 | Flammable Storage Building
0197 | W. P. Garrigus Building
0198 | Multi-Disciplinary Research Lab #3
0199 | Electric Substation #2
0200 | Seaton Center
0202 | Bernard Johnson Student Rec Ctr
0204 | Commonwealth Stadium
0207 | Warren Wright Medical Plaza
0209 | Lucille Caudill Little Fine Arts Library
0210 | T H Morgan Biological Sciences
0211 | Recreation Equipment Storage Building
0212 | Agricultural Distribution Center
0213 | Sanders-Brown Center on Aging
0214 | Farm Maintenance Storage Shed
0215 | College of Nursing
0216 | John W Oswald Building
0217 | Kentucky Tobacco Research and Development Center
0219 | 468 Rose Lane
0220 | Singletary Center for the Arts
0222 | Greg Page Apartments 1
0223 | Greg Page Apartments 2
0224 | Greg Page Apartments 3
0225 | Greg Page Apartments 4
0227 | Greg Page Apartments 5
0229 | Greg Page Apartments 6
0230 | Greg Page Apartments 7
0231 | Greg Page Apartments 8
0232 | Greg Page Apartments 10
0235 | Greg Page Apartments 11
0236 | Greg Page Apartments 12
0237 | Greg Page Apartments 13
0240 | Greg Page Apartments 14
0241 | Greg Page Apartments 15
0243 | Greg Page Apartments 16
0244 | Greg Page Apartments 17
0245 | Greg Page Apartments 18
0246 | Greg Page Apartments 19
0247 | Greg Page Apartments 20
0248 | Greg Page Apartments 21
0249 | Greg Page Apartments 22
0250 | Greg Page Apartments 23
0252 | Greg Page Apartments 24
0253 | Greg Page Apartments 25
0254 | Greg Page Food Storage Laundry
0255 | Communications Building
0256 | Information Building
0257 | Moloney Building
0258 | Bruce Poundstone Regulatory Services Building
0259 | Charles E. Barnhart Building
0260 | Nutter Football Training Facility
0261 | PPD Storage Building
0262 | BIRP Building
0263 | The Football Training Facility
0264 | Oliver H. Raymond Civil Engineering
0265 | Gas Storage Building
0266 | Hagan Baseball Stadium
0267 | Kentucky Clinic
0268 | Nutter Field House
0269 | ASTeCC
0272 | Electric HVAC Building
0274 | PPD Greenhouse
0275 | Hazardous Waste Storage
0276 | UK Hospital - Chandler Medical Center & Hospital
0277 | Gill Heart Institute
0278 | Dental Science Building
0279 | William R. Willard Medical Education Building
0281 | Arboretum Tool Shed
0282 | 154 Bonnie Brae
0283 | Dorotha Smith Oatts Visitor Center
0284 | Arboretum Restrooms
0285 | Peter P. Bosomworth Health Sciences Research Building
0286 | Plant Sciences
0287 | 455 Woodland Ave
0288 | 252 East Maxwell St
0289 | 206 East Maxwell St
0293 | 408 Pennsylvania Ct
0294 | 315 Scott St
0297 | 317 Scott St
0298 | 321 Scott St
0300 | 641 South Limestone St
0301 | Thomas D Clark Building
0302 | 663 South Limestone Garage
0303 | Bingham Davis House
0305 | Raymond F. Betts House
0312 | Max Kade German House and Cultural Center
0314 | 654 Maxwelton Ct
0315 | 624 Maxwelton Ct
0324 | 626 Maxwelton Ct
0325 | 641 Maxwelton Ct
0327 | 643 Maxwelton Ct
0333 | 644 Maxwelton Ct
0336 | 520 Oldham Ct
0337 | 123 State St
0343 | 119 State St
0344 | 400 Pennsylvania Ct
0345 | 402 Pennsylvania Ct
0346 | 405 Pennsylvania Ct
0347 | 406 Pennsylvania Ct
0348 | 410 Pennsylvania Ct
0349 | 319 Rose Lane
0350 | 321 Rose Lane
0351 | 162-164 Gazette Avenue
0353 | Sky Blue Solar House
0355 | 150 Gazette Avenue
0356 | Bus Shelter #1
0361 | Bus Shelter #2
0362 | Bus Shelter #3
0363 | Bus Shelter #7
0365 | Bus Shelter #6
0377 | Bus Shelter #9
0378 | Bus Shelter #10
0381 | Bus Shelter #11
0386 | Ellen H. Richards House
0390 | Weldon House
0391 | 341-343 Scott St
0392 | 403 Pennsylvania Ct
0393 | Softball/Soccer Locker Rooms
0394 | Bus Shelter #12
0397 | 660 South Limestone
0398 | Bus Shelter #4
0399 | Bus Shelter #13
0400 | 424 Euclid Avenue
0401 | Commonwealth House
0402 | William E and Casiana Schmidt Vocal Arts Center
0412 | Ligon House
0413 | John Cropp Softball Stadium
0416 | Hitting Pavilion
0417 | Football Storage Shed
0418 | Shively Grounds Storage Building
0419 | Shively Grounds Building
0420 | W.T. Young Library
0428 | 149 Transcript Ave
0432 | 153 Transcript Ave
0433 | Limestone Park I
0442 | Limestone Park II
0446 | 220 Transcript Ave
0447 | 505 Oldham Ct
0448 | LCC Academic Tech Building
0449 | 408 Linden Walk
0450 | Real Properties Garage
0451 | Boone Tennis Stadium
0452 | 518 Oldham Ct
0453 | Woodland Early Learning Center
0456 | 1117 South Limestone
0460 | Environmental Quality Management
0461 | Stuckert Career Center
0467 | James F. Hardymon Communications Building
0473 | Ralph G Anderson Building (Mech Eng)
0481 | Sigma Chi Fraternity House
0482 | Alpha Tau Omega Fraternity
0484 | Robert Straus Behavioral Research Building
0485 | Sigma Alpha Epsilon Fraternity
0487 | Biomedical Biological Sciences Research Building
0488 | Central Utility Plant #4
0489 | College of Medicine Learning Center
0490 | BBSRB Generator Building
0494 | 630 South Broadway
0495 | John T. Smith Hall
0503 | Dale E. Baldwin Hall
0504 | Margaret Ingels Hall
0505 | David P. Roselle Hall
0506 | Parking Structure #6
0507 | Parking Structure #7
0509 | University Health Service
0514 | Baseball Training Pavilion
0517 | Storage Shed
0518 | Bio-Pharm (BP)
0564 | 413 Pennsylvania Ct
0565 | Parking Structure #8
0566 | Pavilion A
0567 | Joe Craft Center
0568 | 788 Press Avenue
0571 | 792 Press Avenue
0572 | 796 Press Avenue
0582 | 800 Press Avenue
0585 | Medical Office Building (Samaritan)
0592 | Samaritan Chiller Building
0596 | Samaritan Parking Structure
0600 | Seaton Center Storage
0601 | 118 Conn Terrace
0602 | MacAdam Student Observatory
0604 | 102 Conn Terrace
0607 | 104 Conn Terrace
0608 | 108 Conn Terrace
0609 | 110 Conn Terrace
0610 | 120 Conn Terrace
0611 | 1105 S. Limestone
0612 | 1119 S. Limestone
0613 | Air Medical Crew Quarters
0614 | Davis Marksbury Building
0615 | 411 Pennsylvania Court
0616 | 1041 S. Limestone St.
0617 | 1045 S. Limestone St
0618 | 409 Pennsylvania Ct
0619 | Wildcat Coal Lodge
0621 | 179 Leader Ave
0622 | 404 Pennsylvania Ct
0623 | 213 Transcript Ave
0624 | 221 Transcript Ave
0625 | 217 Transcript Ave
0626 | Mandrell Hall
0630 | Bosworth Hall
0631 | Sanders Hall
0633 | Building 100
0636 | Building 200
0637 | Building 300
0639 | Building 400
0641 | Maintenance Bldg.
0644 | Gas Building
0645 | Maxwelton Ct. Apts #1
0646 | Maxwelton Ct. Apts #2
0647 | Maxwelton Ct. Apts #3
0648 | Maxwelton Ct. Apts #4
0649 | Maxwelton Ct. Apts #5
0650 | Maxwelton Ct. Apts #6
1200 | Maxwelton Ct. Apts #7
1201 | Maxwelton Ct. Apts #8
8633 | Maxwelton Ct. Apts #9
9127 | Maxwelton Ct. Apts #10
9813 | Maxwelton Ct. Apts #11
9925 | Maxwelton Ct. Apts #12
9983 | Maxwelton Ct. Apts #13
Maxwelton Ct. Apts #14
Maxwelton Ct. Apts #15
Maxwelton Ct. Apts #16
Electric Substation #1
Electric Substation #3
UK HealthCare Good Samaritan Hospital
1101 S. Limestone
Child Development Center of the Bluegrass, Inc.
Royal Lexington
Shriners-4th & 5th Floors
Anthropology Research Building
Alpha Phi Sorority
College of Medicine Building
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0