## KD Changes
Building ID | 0698 |  |  |  | Status Date: | 2019-12-12 | 2019-12-06 |  | # of Rooms Waiting for eBARS Tags | # of Rooms Waiting for Door Signs |  |  |  | Verified By: | Date:
Name | Waller Health Care Annex 1 |  |  |  | CAD Operator | Aaron Newell | jes |  | 22 | 22
Renovation requires new signage and eBARS tags. Some room numbers are in new locations.
Room ID | Floor | Description of Change | Change to SqFt | Old SqFt | New SqFt | eBARS Tag Status | Door Signage | Comments | eBARS Tag Progress | Date | Issues | New Sign Progress | Date | Issues
GSF | 00 | Sq ft Correction | Yes | 10747 | 10761 | N/A | N/A
000 | 00 | Room Created | Yes | 0 | 1276 | New Tag Required | New Sign Required
000A | 00 | Room Created | Yes | 0 | 137 | New Tag Required | New Sign Required
000B | 00 | Room Created | Yes | 0 | 64 | New Tag Required | New Sign Required
001 | 00 | Room Created | Yes | 0 | 40 | New Tag Required | New Sign Required
002 | 00 | Room Created | Yes | 0 | 18 | New Tag Required | New Sign Required
002A | 00 | Room Created | Yes | 0 | 100 | New Tag Required | New Sign Required
003 | 00 | Room Created | Yes | 0 | 77 | New Tag Required | New Sign Required
004 | 00 | Room Created | Yes | 0 | 55 | New Tag Required | New Sign Required
004A | 00 | Room Created | Yes | 0 | 93 | New Tag Required | New Sign Required
004A1 | 00 | Room Created | Yes | 0 | 160 | New Tag Required | New Sign Required
005 | 00 | Room Created | Yes | 0 | 222 | New Tag Required | New Sign Required
006 | 00 | Room Created | Yes | 0 | 148 | New Tag Required | New Sign Required
006A | 00 | Room Created | Yes | 0 | 101 | New Tag Required | New Sign Required
006B | 00 | Room Created | Yes | 0 | 103 | New Tag Required | New Sign Required
006C | 00 | Room Created | Yes | 0 | 103 | New Tag Required | New Sign Required
006E | 00 | Room Created | Yes | 0 | 127 | New Tag Required | New Sign Required
006F | 00 | Room Created | Yes | 0 | 112 | New Tag Required | New Sign Required
006G | 00 | Room Created | Yes | 0 | 112 | New Tag Required | New Sign Required
007 | 00 | Room Created | Yes | 0 | 254 | New Tag Required | New Sign Required
008 | 00 | Room Created | Yes | 0 | 546 | New Tag Required | New Sign Required
008A | 00 | Room Created | Yes | 0 | 117 | New Tag Required | New Sign Required
009 | 00 | Room Created | Yes | 0 | 254 | New Tag Required | New Sign Required
010 | 00 | Room Created | Yes | 0 | 75 | New Tag Required | New Sign Required
011 | 00 | Room Created | Yes | 0 | 723 | New Tag Required | New Sign Required
014 | 00 | Room Created | Yes | 0 | 689 | New Tag Required | New Sign Required
015 | 00 | Room Created | Yes | 0 | 737 | New Tag Required | New Sign Required
018 | 00 | Room Created | Yes | 0 | 719 | New Tag Required | New Sign Required
019 | 00 | Room Created | Yes | 0 | 737 | New Tag Required | New Sign Required
020 | 00 | Room Created | Yes | 0 | 83 | New Tag Required | New Sign Required
022 | 00 | Room Created | Yes | 0 | 339 | New Tag Required | New Sign Required
022A | 00 | Room Created | Yes | 0 | 26 | New Tag Required | New Sign Required
023 | 00 | Room Created | Yes | 0 | 723 | New Tag Required | New Sign Required
050 | 00 | Delete This Room Number | Yes | 894 | 0 | N/A | N/A
050A | 00 | Delete This Room Number | Yes | 34 | 0 | N/A | N/A
050B | 00 | Delete This Room Number | Yes | 20 | 0 | N/A | N/A
050C | 00 | Delete This Room Number | Yes | 20 | 0 | N/A | N/A
051 | 00 | Delete This Room Number | Yes | 473 | 0 | N/A | N/A
053 | 00 | Delete This Room Number | Yes | 6566 | 0 | N/A | N/A
054 | 00 | Delete This Room Number | Yes | 1035 | 0 | N/A | N/A
055 | 00 | Delete This Room Number | Yes | 469 | 0 | N/A | N/A
ST0000A | 00 | Sq ft Correction | Yes | 164 | 168 | No Change | No Change | Verify need for tags and signs
ST0000B | 00 | Sq ft Correction | Yes | 170 | 174 | No Change | No Change | Verify need for tags and signs
EL0000A | 00 | Sq ft Correction | Yes | 54 | 55 | No Change | No Change | Verify need for tags and signs
GSF | 01 | Sq ft Correction | Yes | 11742 | 11678 | N/A | N/A
100 | 01 | Sq ft Correction | Yes | 896 | 789 | New Tag Required | New Sign Required
100A | 01 | Room Created | Yes | 0 | 96 | New Tag Required | New Sign Required
100B | 01 | Room Created | Yes | 0 | 113 | New Tag Required | New Sign Required
101 | 01 | Room Created | Yes | 0 | 266 | New Tag Required | New Sign Required
102 | 01 | Room Created | Yes | 0 | 1625 | New Tag Required | New Sign Required
103 | 01 | Room Created | Yes | 0 | 268 | New Tag Required | New Sign Required
105 | 01 | Room Created | Yes | 0 | 71 | New Tag Required | New Sign Required
106 | 01 | Room Created | Yes | 0 | 300 | New Tag Required | New Sign Required
107 | 01 | Room Created | Yes | 0 | 291 | New Tag Required | New Sign Required
108 | 01 | Room Created | Yes | 0 | 319 | New Tag Required | New Sign Required
108A | 01 | Room Created | Yes | 0 | 98 | New Tag Required | New Sign Required
108B | 01 | Room Created | Yes | 0 | 99 | New Tag Required | New Sign Required
108C | 01 | Room Created | Yes | 0 | 99 | New Tag Required | New Sign Required
108D | 01 | Room Created | Yes | 0 | 95 | New Tag Required | New Sign Required
108G | 01 | Room Created | Yes | 0 | 97 | New Tag Required | New Sign Required
108H | 01 | Room Created | Yes | 0 | 137 | New Tag Required | New Sign Required
108J | 01 | Room Created | Yes | 0 | 99 | New Tag Required | New Sign Required
108K | 01 | Room Created | Yes | 0 | 98 | New Tag Required | New Sign Required
108L | 01 | Room Created | Yes | 0 | 27 | New Tag Required | New Sign Required
108M | 01 | Room Created | Yes | 0 | 250 | New Tag Required | New Sign Required
109 | 01 | Room Created | Yes | 0 | 383 | New Tag Required | New Sign Required
109A | 01 | Room Created | Yes | 0 | 114 | New Tag Required | New Sign Required
109B | 01 | Room Created | Yes | 0 | 121 | New Tag Required | New Sign Required
113 | 01 | Room Created | Yes | 0 | 355 | New Tag Required | New Sign Required
113A | 01 | Room Created | Yes | 0 | 122 | New Tag Required | New Sign Required
115 | 01 | Room Created | Yes | 0 | 735 | New Tag Required | New Sign Required
116 | 01 | Room Created | Yes | 0 | 783 | New Tag Required | New Sign Required
116A | 01 | Room Created | Yes | 0 | 121 | New Tag Required | New Sign Required
119 | 01 | Room Created | Yes | 0 | 736 | New Tag Required | New Sign Required
120 | 01 | Room Created | Yes | 0 | 239 | New Tag Required | New Sign Required
122 | 01 | Room Created | Yes | 0 | 34 | New Tag Required | New Sign Required
123 | 01 | Room Created | Yes | 0 | 358 | New Tag Required | New Sign Required
126 | 01 | Delete This Room Number | Yes | 31 | 0 | N/A | N/A
0150 | 01 | Delete This Room Number | Yes | 1142 | 0 | N/A | N/A
0150A | 01 | Delete This Room Number | Yes | 267 | 0 | N/A | N/A
0150B | 01 | Delete This Room Number | Yes | 134 | 0 | N/A | N/A
0150B1 | 01 | Delete This Room Number | Yes | 80 | 0 | N/A | N/A
0150C | 01 | Delete This Room Number | Yes | 366 | 0 | N/A | N/A
0151 | 01 | Delete This Room Number | Yes | 1204 | 0 | N/A | N/A
0151D | 01 | Delete This Room Number | Yes | 241 | 0 | N/A | N/A
0151D1 | 01 | Delete This Room Number | Yes | 51 | 0 | N/A | N/A
0152A | 01 | Delete This Room Number | Yes | 340 | 0 | N/A | N/A
0152B | 01 | Delete This Room Number | Yes | 705 | 0 | N/A | N/A
0153A | 01 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0153A1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0153B | 01 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0153B1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0153C | 01 | Delete This Room Number | Yes | 303 | 0 | N/A | N/A
0153C1 | 01 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0154A | 01 | Delete This Room Number | Yes | 293 | 0 | N/A | N/A
0154A1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0154B | 01 | Delete This Room Number | Yes | 633 | 0 | N/A | N/A
0154C | 01 | Delete This Room Number | Yes | 95 | 0 | N/A | N/A
0154D | 01 | Delete This Room Number | Yes | 373 | 0 | N/A | N/A
0154D1 | 01 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0155A | 01 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0155A1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0155B | 01 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0155B1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0155C | 01 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0155C1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0155D | 01 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0155D1 | 01 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
ST0100A | 01 | Sq ft Correction | Yes | 164 | 208 | No Change | No Change | Verify need for tags and signs
ST0100B | 01 | Sq ft Correction | Yes | 170 | 213 | No Change | No Change | Verify need for tags and signs
EL0100A | 01 | Sq ft Correction | Yes | 54 | 55 | No Change | No Change | Verify need for tags and signs
XA0101 | 01 | Sq ft Correction | Yes | 884 | 779 | No Change | No Change | Exterior Canopy
GSF | 02 | Sq ft Correction | Yes | 10745 | 10763 | N/A | N/A
200 | 02 | Sq ft Correction | Yes | 1283 | 1255 | New Tag Required | New Sign Required
200A | 02 | Room Created | Yes | 0 | 113 | New Tag Required | New Sign Required
201 | 02 | Room Created | Yes | 0 | 273 | New Tag Required | New Sign Required
202 | 02 | Room Created | Yes | 0 | 317 | New Tag Required | New Sign Required
203 | 02 | Room Created | Yes | 0 | 275 | New Tag Required | New Sign Required
204 | 02 | Room Created | Yes | 0 | 962 | New Tag Required | New Sign Required
204A | 02 | Room Created | Yes | 0 | 108 | New Tag Required | New Sign Required
204B | 02 | Room Created | Yes | 0 | 163 | New Tag Required | New Sign Required
204C | 02 | Room Created | Yes | 0 | 114 | New Tag Required | New Sign Required
204D | 02 | Room Created | Yes | 0 | 121 | New Tag Required | New Sign Required
204E | 02 | Room Created | Yes | 0 | 117 | New Tag Required | New Sign Required
204F | 02 | Room Created | Yes | 0 | 117 | New Tag Required | New Sign Required
204G | 02 | Room Created | Yes | 0 | 109 | New Tag Required | New Sign Required
205 | 02 | Room Created | Yes | 0 | 71 | New Tag Required | New Sign Required
207 | 02 | Room Created | Yes | 0 | 291 | New Tag Required | New Sign Required
209 | 02 | Room Created | Yes | 0 | 1333 | New Tag Required | New Sign Required
209A | 02 | Room Created | Yes | 0 | 179 | New Tag Required | New Sign Required
209D | 02 | Room Created | Yes | 0 | 117 | New Tag Required | New Sign Required
209E | 02 | Room Created | Yes | 0 | 109 | New Tag Required | New Sign Required
212 | 02 | Room Created | Yes | 0 | 166 | New Tag Required | New Sign Required
216 | 02 | Room Created | Yes | 0 | 1218 | New Tag Required | New Sign Required
216A | 02 | Room Created | Yes | 0 | 166 | New Tag Required | New Sign Required
216B | 02 | Room Created | Yes | 0 | 113 | New Tag Required | New Sign Required
216C | 02 | Room Created | Yes | 0 | 101 | New Tag Required | New Sign Required
219 | 02 | Room Created | Yes | 0 | 112 | New Tag Required | New Sign Required
219A | 02 | Room Created | Yes | 0 | 112 | New Tag Required | New Sign Required
219B | 02 | Room Created | Yes | 0 | 120 | New Tag Required | New Sign Required
219C | 02 | Room Created | Yes | 0 | 120 | New Tag Required | New Sign Required
219D | 02 | Room Created | Yes | 0 | 126 | New Tag Required | New Sign Required
219E | 02 | Room Created | Yes | 0 | 127 | New Tag Required | New Sign Required
219F | 02 | Room Created | Yes | 0 | 125 | New Tag Required | New Sign Required
219G | 02 | Room Created | Yes | 0 | 355 | New Tag Required | New Sign Required
220 | 02 | Room Created | Yes | 0 | 101 | New Tag Required | New Sign Required
222 | 02 | Room Created | Yes | 0 | 34 | New Tag Required | New Sign Required
226 | 02 | Delete This Room Number | Yes | 31 | 0 | N/A | N/A
0250A | 02 | Delete This Room Number | Yes | 310 | 0 | N/A | N/A
0250A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0250B | 02 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0250B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0250C | 02 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0250C1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0250D | 02 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0250D1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0251A | 02 | Delete This Room Number | Yes | 364 | 0 | N/A | N/A
0251A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0251B | 02 | Delete This Room Number | Yes | 309 | 0 | N/A | N/A
0251B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0251C | 02 | Delete This Room Number | Yes | 320 | 0 | N/A | N/A
0251C1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0251D | 02 | Delete This Room Number | Yes | 302 | 0 | N/A | N/A
0251D1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0252A | 02 | Delete This Room Number | Yes | 290 | 0 | N/A | N/A
0252A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0252B | 02 | Delete This Room Number | Yes | 295 | 0 | N/A | N/A
0252B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0252C | 02 | Delete This Room Number | Yes | 306 | 0 | N/A | N/A
0252C1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0253A | 02 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0253A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0253B | 02 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0253B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0253C | 02 | Delete This Room Number | Yes | 302 | 0 | N/A | N/A
0253C1 | 02 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0254A | 02 | Delete This Room Number | Yes | 295 | 0 | N/A | N/A
0254A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0254B | 02 | Delete This Room Number | Yes | 309 | 0 | N/A | N/A
0254B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0254C | 02 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0254C1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0254D | 02 | Delete This Room Number | Yes | 374 | 0 | N/A | N/A
0254D1 | 02 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0255A | 02 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0255A1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0255B | 02 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0255B1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0255C | 02 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0255C1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0255D | 02 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0255D1 | 02 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
ST0200A | 02 | Sq ft Correction | Yes | 164 | 164 | No Change | No Change | Verify need for tags and signs
ST0200B | 02 | Sq ft Correction | Yes | 170 | 170 | No Change | No Change | Verify need for tags and signs
EL0200A | 02 | Sq ft Correction | Yes | 54 | 55 | No Change | No Change | Verify need for tags and signs
GSF | 03 | Sq ft Correction | Yes | 10763 | 10746 | N/A | N/A
300 | 03 | Sq ft Correction | Yes | 1283 | 1211 | New Tag Required | New Sign Required
300A | 03 | Room Created | Yes | 0 | 113 | New Tag Required | New Sign Required
301 | 03 | Room Created | Yes | 0 | 273 | New Tag Required | New Sign Required
302 | 03 | Room Created | Yes | 0 | 317 | New Tag Required | New Sign Required
303 | 03 | Room Created | Yes | 0 | 275 | New Tag Required | New Sign Required
304 | 03 | Room Created | Yes | 0 | 151 | New Tag Required | New Sign Required
304A | 03 | Room Created | Yes | 0 | 197 | New Tag Required | New Sign Required
304B | 03 | Room Created | Yes | 0 | 125 | New Tag Required | New Sign Required
304C | 03 | Room Created | Yes | 0 | 127 | New Tag Required | New Sign Required
304D | 03 | Room Created | Yes | 0 | 114 | New Tag Required | New Sign Required
305 | 03 | Room Created | Yes | 0 | 71 | New Tag Required | New Sign Required
306 | 03 | Room Created | Yes | 0 | 115 | New Tag Required | New Sign Required
307 | 03 | Room Created | Yes | 0 | 291 | New Tag Required | New Sign Required
308 | 03 | Room Created | Yes | 0 | 726 | New Tag Required | New Sign Required
308A | 03 | Room Created | Yes | 0 | 122 | New Tag Required | New Sign Required
308B | 03 | Room Created | Yes | 0 | 134 | New Tag Required | New Sign Required
309A | 03 | Room Created | Yes | 0 | 125 | New Tag Required | New Sign Required
309B | 03 | Room Created | Yes | 0 | 126 | New Tag Required | New Sign Required
309C | 03 | Room Created | Yes | 0 | 125 | New Tag Required | New Sign Required
316 | 03 | Room Created | Yes | 0 | 1107 | New Tag Required | New Sign Required
316A | 03 | Room Created | Yes | 0 | 134 | New Tag Required | New Sign Required
316B | 03 | Room Created | Yes | 0 | 122 | New Tag Required | New Sign Required
316C | 03 | Room Created | Yes | 0 | 114 | New Tag Required | New Sign Required
317 | 03 | Room Created | Yes | 0 | 1523 | New Tag Required | New Sign Required
317A | 03 | Room Created | Yes | 0 | 125 | New Tag Required | New Sign Required
317B | 03 | Room Created | Yes | 0 | 126 | New Tag Required | New Sign Required
317C | 03 | Room Created | Yes | 0 | 126 | New Tag Required | New Sign Required
320 | 03 | Room Created | Yes | 0 | 275 | New Tag Required | New Sign Required
320A | 03 | Room Created | Yes | 0 | 135 | New Tag Required | New Sign Required
321 | 03 | Room Created | Yes | 0 | 719 | New Tag Required | New Sign Required
322 | 03 | Room Created | Yes | 0 | 34 | New Tag Required | New Sign Required
326 | 03 | Delete This Room Number | Yes | 31 | 0 | N/A | N/A
0350A | 03 | Delete This Room Number | Yes | 310 | 0 | N/A | N/A
0350A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0350B | 03 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0350B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0350C | 03 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0350C1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0350D | 03 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0350D1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0351A | 03 | Delete This Room Number | Yes | 364 | 0 | N/A | N/A
0351A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0351B | 03 | Delete This Room Number | Yes | 309 | 0 | N/A | N/A
0351B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0351C | 03 | Delete This Room Number | Yes | 320 | 0 | N/A | N/A
0351C1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0351D | 03 | Delete This Room Number | Yes | 302 | 0 | N/A | N/A
0351D1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0352A | 03 | Delete This Room Number | Yes | 290 | 0 | N/A | N/A
0352A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0352B | 03 | Delete This Room Number | Yes | 295 | 0 | N/A | N/A
0352B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0352C | 03 | Delete This Room Number | Yes | 306 | 0 | N/A | N/A
0352C1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0353A | 03 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0353A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0353B | 03 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0353B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0353C | 03 | Delete This Room Number | Yes | 302 | 0 | N/A | N/A
0353C1 | 03 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0354A | 03 | Delete This Room Number | Yes | 295 | 0 | N/A | N/A
0354A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0354B | 03 | Delete This Room Number | Yes | 309 | 0 | N/A | N/A
0354B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0354C | 03 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0354C1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0354D | 03 | Delete This Room Number | Yes | 374 | 0 | N/A | N/A
0354D1 | 03 | Delete This Room Number | Yes | 46 | 0 | N/A | N/A
0355A | 03 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0355A1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0355B | 03 | Delete This Room Number | Yes | 321 | 0 | N/A | N/A
0355B1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0355C | 03 | Delete This Room Number | Yes | 308 | 0 | N/A | N/A
0355C1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
0355D | 03 | Delete This Room Number | Yes | 307 | 0 | N/A | N/A
0355D1 | 03 | Delete This Room Number | Yes | 42 | 0 | N/A | N/A
ST0300A | 03 | Sq ft Correction | Yes | 164 | 116 | No Change | No Change | Verify need for tags and signs
ST0300B | 03 | Sq ft Correction | Yes | 170 | 121 | No Change | No Change | Verify need for tags and signs
EL0300A | 03 | Sq ft Correction | Yes | 54 | 55 | No Change | No Change | Verify need for tags and signs
[6 empty] | Total Tags Required | Total Signs Required |  | Total Tags Installed |  |  | Total Signs Installed
[6 empty] | 22 | 22 |  | 0 |  |  | 0
End of Data Validation

## SAP Changes
Building ID | 0698 |  | Status Date: | 2019-12-12 | 2019-12-06
Name | Waller Health Care Annex 1 |  | CAD Operator | Aaron Newell | jes
SAP Functional Location | Room Description | Action | SqFt | Comments
LX-0698-00-00050 | Waller Health 1 - Bsmt Room 050 | Deactivate | 0
LX-0698-00-00050A | Waller Health 1 - Bsmt Room 050A | Deactivate | 0
LX-0698-00-00050B | Waller Health 1 - Bsmt Room 050B | Deactivate | 0
LX-0698-00-00050C | Waller Health 1 - Bsmt Room 050C | Deactivate | 0
LX-0698-00-00051 | Waller Health 1 - Bsmt Room 051 | Deactivate | 0
LX-0698-00-00053 | Waller Health 1 - Bsmt Room 053 | Deactivate | 0
LX-0698-00-00054 | Waller Health 1 - Bsmt Room 054 | Deactivate | 0
LX-0698-00-00055 | Waller Health 1 - Bsmt Room 055 | Deactivate | 0
LX-0698-01-0126 | Waller Health 1 - 1st Flr Room 126 | Deactivate | 0
LX-0698-01-0150 | Waller Health 1 - 1st Flr Room 150 | Deactivate | 0
LX-0698-01-0150A | Waller Health 1 - 1st Flr Room 150A | Deactivate | 0
LX-0698-01-0150B | Waller Health 1 - 1st Flr Room 150B | Deactivate | 0
LX-0698-01-0150B1 | Waller Health 1 - 1st Flr Room 150B1 | Deactivate | 0
LX-0698-01-0150C | Waller Health 1 - 1st Flr Room 150C | Deactivate | 0
LX-0698-01-0151 | Waller Health 1 - 1st Flr Room 151 | Deactivate | 0
LX-0698-01-0151D | Waller Health 1 - 1st Flr Room 151D | Deactivate | 0
LX-0698-01-0151D1 | Waller Health 1 - 1st Flr Room 151D1 | Deactivate | 0
LX-0698-01-0152A | Waller Health 1 - 1st Flr Room 152A | Deactivate | 0
LX-0698-01-0152B | Waller Health 1 - 1st Flr Room 152B | Deactivate | 0
LX-0698-01-0153A | Waller Health 1 - 1st Flr Room 153A | Deactivate | 0
LX-0698-01-0153A1 | Waller Health 1 - 1st Flr Room 153A1 | Deactivate | 0
LX-0698-01-0153B | Waller Health 1 - 1st Flr Room 153B | Deactivate | 0
LX-0698-01-0153B1 | Waller Health 1 - 1st Flr Room 153B1 | Deactivate | 0
LX-0698-01-0153C | Waller Health 1 - 1st Flr Room 153C | Deactivate | 0
LX-0698-01-0153C1 | Waller Health 1 - 1st Flr Room 153C1 | Deactivate | 0
LX-0698-01-0154A | Waller Health 1 - 1st Flr Room 154A | Deactivate | 0
LX-0698-01-0154A1 | Waller Health 1 - 1st Flr Room 154A1 | Deactivate | 0
LX-0698-01-0154B | Waller Health 1 - 1st Flr Room 154B | Deactivate | 0
LX-0698-01-0154C | Waller Health 1 - 1st Flr Room 154C | Deactivate | 0
LX-0698-01-0154D | Waller Health 1 - 1st Flr Room 154D | Deactivate | 0
LX-0698-01-0154D1 | Waller Health 1 - 1st Flr Room 154D1 | Deactivate | 0
LX-0698-01-0155A | Waller Health 1 - 1st Flr Room 155A | Deactivate | 0
LX-0698-01-0155A1 | Waller Health 1 - 1st Flr Room 155A1 | Deactivate | 0
LX-0698-01-0155B | Waller Health 1 - 1st Flr Room 155B | Deactivate | 0
LX-0698-01-0155B1 | Waller Health 1 - 1st Flr Room 155B1 | Deactivate | 0
LX-0698-01-0155C | Waller Health 1 - 1st Flr Room 155C | Deactivate | 0
LX-0698-01-0155C1 | Waller Health 1 - 1st Flr Room 155C1 | Deactivate | 0
LX-0698-01-0155D | Waller Health 1 - 1st Flr Room 155D | Deactivate | 0
LX-0698-01-0155D1 | Waller Health 1 - 1st Flr Room 155D1 | Deactivate | 0
LX-0698-02-0226 | Waller Health 1 - 2nd Flr Room 226 | Deactivate | 0
LX-0698-02-0250A | Waller Health 1 - 2nd Flr Room 250A | Deactivate | 0
LX-0698-02-0250A1 | Waller Health 1 - 2nd Flr Room 250A1 | Deactivate | 0
LX-0698-02-0250B | Waller Health 1 - 2nd Flr Room 250B | Deactivate | 0
LX-0698-02-0250B1 | Waller Health 1 - 2nd Flr Room 250B1 | Deactivate | 0
LX-0698-02-0250C | Waller Health 1 - 2nd Flr Room 250C | Deactivate | 0
LX-0698-02-0250C1 | Waller Health 1 - 2nd Flr Room 250C1 | Deactivate | 0
LX-0698-02-0250D | Waller Health 1 - 2nd Flr Room 250D | Deactivate | 0
LX-0698-02-0250D1 | Waller Health 1 - 2nd Flr Room 250D1 | Deactivate | 0
LX-0698-02-0251A | Waller Health 1 - 2nd Flr Room 251A | Deactivate | 0
LX-0698-02-0251A1 | Waller Health 1 - 2nd Flr Room 251A1 | Deactivate | 0
LX-0698-02-0251B | Waller Health 1 - 2nd Flr Room 251B | Deactivate | 0
LX-0698-02-0251B1 | Waller Health 1 - 2nd Flr Room 251B1 | Deactivate | 0
LX-0698-02-0251C | Waller Health 1 - 2nd Flr Room 251C | Deactivate | 0
LX-0698-02-0251C1 | Waller Health 1 - 2nd Flr Room 251C1 | Deactivate | 0
LX-0698-02-0251D | Waller Health 1 - 2nd Flr Room 251D | Deactivate | 0
LX-0698-02-0251D1 | Waller Health 1 - 2nd Flr Room 251D1 | Deactivate | 0
LX-0698-02-0252A | Waller Health 1 - 2nd Flr Room 252A | Deactivate | 0
LX-0698-02-0252A1 | Waller Health 1 - 2nd Flr Room 252A1 | Deactivate | 0
LX-0698-02-0252B | Waller Health 1 - 2nd Flr Room 252B | Deactivate | 0
LX-0698-02-0252B1 | Waller Health 1 - 2nd Flr Room 252B1 | Deactivate | 0
LX-0698-02-0252C | Waller Health 1 - 2nd Flr Room 252C | Deactivate | 0
LX-0698-02-0252C1 | Waller Health 1 - 2nd Flr Room 252C1 | Deactivate | 0
LX-0698-02-0253A | Waller Health 1 - 2nd Flr Room 253A | Deactivate | 0
LX-0698-02-0253A1 | Waller Health 1 - 2nd Flr Room 253A1 | Deactivate | 0
LX-0698-02-0253B | Waller Health 1 - 2nd Flr Room 253B | Deactivate | 0
LX-0698-02-0253B1 | Waller Health 1 - 2nd Flr Room 253B1 | Deactivate | 0
LX-0698-02-0253C | Waller Health 1 - 2nd Flr Room 253C | Deactivate | 0
LX-0698-02-0253C1 | Waller Health 1 - 2nd Flr Room 253C1 | Deactivate | 0
LX-0698-02-0254A | Waller Health 1 - 2nd Flr Room 254A | Deactivate | 0
LX-0698-02-0254A1 | Waller Health 1 - 2nd Flr Room 254A1 | Deactivate | 0
LX-0698-02-0254B | Waller Health 1 - 2nd Flr Room 254B | Deactivate | 0
LX-0698-02-0254B1 | Waller Health 1 - 2nd Flr Room 254B1 | Deactivate | 0
LX-0698-02-0254C | Waller Health 1 - 2nd Flr Room 254C | Deactivate | 0
LX-0698-02-0254C1 | Waller Health 1 - 2nd Flr Room 254C1 | Deactivate | 0
LX-0698-02-0254D | Waller Health 1 - 2nd Flr Room 254D | Deactivate | 0
LX-0698-02-0254D1 | Waller Health 1 - 2nd Flr Room 254D1 | Deactivate | 0
LX-0698-02-0255A | Waller Health 1 - 2nd Flr Room 255A | Deactivate | 0
LX-0698-02-0255A1 | Waller Health 1 - 2nd Flr Room 255A1 | Deactivate | 0
LX-0698-02-0255B | Waller Health 1 - 2nd Flr Room 255B | Deactivate | 0
LX-0698-02-0255B1 | Waller Health 1 - 2nd Flr Room 255B1 | Deactivate | 0
LX-0698-02-0255C | Waller Health 1 - 2nd Flr Room 255C | Deactivate | 0
LX-0698-02-0255C1 | Waller Health 1 - 2nd Flr Room 255C1 | Deactivate | 0
LX-0698-02-0255D | Waller Health 1 - 2nd Flr Room 255D | Deactivate | 0
LX-0698-02-0255D1 | Waller Health 1 - 2nd Flr Room 255D1 | Deactivate | 0
LX-0698-03-0326 | Waller Health 1 - 3rd Flr Room 326 | Deactivate | 0
LX-0698-03-0350A | Waller Health 1 - 3rd Flr Room 350A | Deactivate | 0
LX-0698-03-0350A1 | Waller Health 1 - 3rd Flr Room 350A1 | Deactivate | 0
LX-0698-03-0350B | Waller Health 1 - 3rd Flr Room 350B | Deactivate | 0
LX-0698-03-0350B1 | Waller Health 1 - 3rd Flr Room 350B1 | Deactivate | 0
LX-0698-03-0350C | Waller Health 1 - 3rd Flr Room 350C | Deactivate | 0
LX-0698-03-0350C1 | Waller Health 1 - 3rd Flr Room 350C1 | Deactivate | 0
LX-0698-03-0350D | Waller Health 1 - 3rd Flr Room 350D | Deactivate | 0
LX-0698-03-0350D1 | Waller Health 1 - 3rd Flr Room 350D1 | Deactivate | 0
LX-0698-03-0351A | Waller Health 1 - 3rd Flr Room 351A | Deactivate | 0
LX-0698-03-0351A1 | Waller Health 1 - 3rd Flr Room 351A1 | Deactivate | 0
LX-0698-03-0351B | Waller Health 1 - 3rd Flr Room 351B | Deactivate | 0
LX-0698-03-0351B1 | Waller Health 1 - 3rd Flr Room 351B1 | Deactivate | 0
LX-0698-03-0351C | Waller Health 1 - 3rd Flr Room 351C | Deactivate | 0
LX-0698-03-0351C1 | Waller Health 1 - 3rd Flr Room 351C1 | Deactivate | 0
LX-0698-03-0351D | Waller Health 1 - 3rd Flr Room 351D | Deactivate | 0
LX-0698-03-0351D1 | Waller Health 1 - 3rd Flr Room 351D1 | Deactivate | 0
LX-0698-03-0352A | Waller Health 1 - 3rd Flr Room 352A | Deactivate | 0
LX-0698-03-0352A1 | Waller Health 1 - 3rd Flr Room 352A1 | Deactivate | 0
LX-0698-03-0352B | Waller Health 1 - 3rd Flr Room 352B | Deactivate | 0
LX-0698-03-0352B1 | Waller Health 1 - 3rd Flr Room 352B1 | Deactivate | 0
LX-0698-03-0352C | Waller Health 1 - 3rd Flr Room 352C | Deactivate | 0
LX-0698-03-0352C1 | Waller Health 1 - 3rd Flr Room 352C1 | Deactivate | 0
LX-0698-03-0353A | Waller Health 1 - 3rd Flr Room 353A | Deactivate | 0
LX-0698-03-0353A1 | Waller Health 1 - 3rd Flr Room 353A1 | Deactivate | 0
LX-0698-03-0353B | Waller Health 1 - 3rd Flr Room 353B | Deactivate | 0
LX-0698-03-0353B1 | Waller Health 1 - 3rd Flr Room 353B1 | Deactivate | 0
LX-0698-03-0353C | Waller Health 1 - 3rd Flr Room 353C | Deactivate | 0
LX-0698-03-0353C1 | Waller Health 1 - 3rd Flr Room 353C1 | Deactivate | 0
LX-0698-03-0354A | Waller Health 1 - 3rd Flr Room 354A | Deactivate | 0
LX-0698-03-0354A1 | Waller Health 1 - 3rd Flr Room 354A1 | Deactivate | 0
LX-0698-03-0354B | Waller Health 1 - 3rd Flr Room 354B | Deactivate | 0
LX-0698-03-0354B1 | Waller Health 1 - 3rd Flr Room 354B1 | Deactivate | 0
LX-0698-03-0354C | Waller Health 1 - 3rd Flr Room 354C | Deactivate | 0
LX-0698-03-0354C1 | Waller Health 1 - 3rd Flr Room 354C1 | Deactivate | 0
LX-0698-03-0354D | Waller Health 1 - 3rd Flr Room 354D | Deactivate | 0
LX-0698-03-0354D1 | Waller Health 1 - 3rd Flr Room 354D1 | Deactivate | 0
LX-0698-03-0355A | Waller Health 1 - 3rd Flr Room 355A | Deactivate | 0
LX-0698-03-0355A1 | Waller Health 1 - 3rd Flr Room 355A1 | Deactivate | 0
LX-0698-03-0355B | Waller Health 1 - 3rd Flr Room 355B | Deactivate | 0
LX-0698-03-0355B1 | Waller Health 1 - 3rd Flr Room 355B1 | Deactivate | 0
LX-0698-03-0355C | Waller Health 1 - 3rd Flr Room 355C | Deactivate | 0
LX-0698-03-0355C1 | Waller Health 1 - 3rd Flr Room 355C1 | Deactivate | 0
LX-0698-03-0355D | Waller Health 1 - 3rd Flr Room 355D | Deactivate | 0
LX-0698-03-0355D1 | Waller Health 1 - 3rd Flr Room 355D1 | Deactivate | 0
LX-0698-00-0000 | Waller Health 1 - Bsmt Room 000 | Add | 1276
LX-0698-00-0000A | Waller Health 1 - Bsmt Room 000A | Add | 137
LX-0698-00-0000B | Waller Health 1 - Bsmt Room 000B | Add | 64
LX-0698-00-0001 | Waller Health 1 - Bsmt Room 001 | Add | 40
LX-0698-00-0002 | Waller Health 1 - Bsmt Room 002 | Add | 18
LX-0698-00-0002A | Waller Health 1 - Bsmt Room 002A | Add | 100
LX-0698-00-0003 | Waller Health 1 - Bsmt Room 003 | Add | 77
LX-0698-00-0004 | Waller Health 1 - Bsmt Room 004 | Add | 55
LX-0698-00-0004A | Waller Health 1 - Bsmt Room 004A | Add | 93
LX-0698-00-0004A1 | Waller Health 1 - Bsmt Room 004A1 | Add | 160
LX-0698-00-0005 | Waller Health 1 - Bsmt Room 005 | Add | 222
LX-0698-00-0006 | Waller Health 1 - Bsmt Room 006 | Add | 148
LX-0698-00-0006A | Waller Health 1 - Bsmt Room 006A | Add | 101
LX-0698-00-0006B | Waller Health 1 - Bsmt Room 006B | Add | 103
LX-0698-00-0006C | Waller Health 1 - Bsmt Room 006C | Add | 103
LX-0698-00-0006E | Waller Health 1 - Bsmt Room 006E | Add | 127
LX-0698-00-0006F | Waller Health 1 - Bsmt Room 006F | Add | 112
LX-0698-00-0006G | Waller Health 1 - Bsmt Room 006G | Add | 112
LX-0698-00-0007 | Waller Health 1 - Bsmt Room 007 | Add | 254
LX-0698-00-0008 | Waller Health 1 - Bsmt Room 008 | Add | 546
LX-0698-00-0008A | Waller Health 1 - Bsmt Room 008A | Add | 117
LX-0698-00-0009 | Waller Health 1 - Bsmt Room 009 | Add | 254
LX-0698-00-0010 | Waller Health 1 - Bsmt Room 010 | Add | 75
LX-0698-00-0011 | Waller Health 1 - Bsmt Room 011 | Add | 723
LX-0698-00-0014 | Waller Health 1 - Bsmt Room 014 | Add | 689
LX-0698-00-0015 | Waller Health 1 - Bsmt Room 015 | Add | 737
LX-0698-00-0018 | Waller Health 1 - Bsmt Room 018 | Add | 719
LX-0698-00-0019 | Waller Health 1 - Bsmt Room 019 | Add | 737
LX-0698-00-0020 | Waller Health 1 - Bsmt Room 020 | Add | 83
LX-0698-00-0022 | Waller Health 1 - Bsmt Room 022 | Add | 339
LX-0698-00-0022A | Waller Health 1 - Bsmt Room 022A | Add | 26
LX-0698-00-0023 | Waller Health 1 - Bsmt Room 023 | Add | 723
LX-0698-01-0100A | Waller Health 1 - 1st Flr Room 100A | Add | 96
LX-0698-01-0100B | Waller Health 1 - 1st Flr Room 100B | Add | 113
LX-0698-01-0101 | Waller Health 1 - 1st Flr Room 101 | Add | 266
LX-0698-01-0102 | Waller Health 1 - 1st Flr Room 102 | Add | 1625
LX-0698-01-0103 | Waller Health 1 - 1st Flr Room 103 | Add | 268
LX-0698-01-0105 | Waller Health 1 - 1st Flr Room 105 | Add | 71
LX-0698-01-0106 | Waller Health 1 - 1st Flr Room 106 | Add | 300
LX-0698-01-0107 | Waller Health 1 - 1st Flr Room 107 | Add | 291
LX-0698-01-0108 | Waller Health 1 - 1st Flr Room 108 | Add | 319
LX-0698-01-0108A | Waller Health 1 - 1st Flr Room 108A | Add | 98
LX-0698-01-0108B | Waller Health 1 - 1st Flr Room 108B | Add | 99
LX-0698-01-0108C | Waller Health 1 - 1st Flr Room 108C | Add | 99
LX-0698-01-0108D | Waller Health 1 - 1st Flr Room 108D | Add | 95
LX-0698-01-0108G | Waller Health 1 - 1st Flr Room 108G | Add | 97
LX-0698-01-0108H | Waller Health 1 - 1st Flr Room 108H | Add | 137
LX-0698-01-0108J | Waller Health 1 - 1st Flr Room 108J | Add | 99
LX-0698-01-0108K | Waller Health 1 - 1st Flr Room 108K | Add | 98
LX-0698-01-0108L | Waller Health 1 - 1st Flr Room 108L | Add | 27
LX-0698-01-0108M | Waller Health 1 - 1st Flr Room 108M | Add | 250
LX-0698-01-0109 | Waller Health 1 - 1st Flr Room 109 | Add | 383
LX-0698-01-0109A | Waller Health 1 - 1st Flr Room 109A | Add | 114
LX-0698-01-0109B | Waller Health 1 - 1st Flr Room 109B | Add | 121
LX-0698-01-0113 | Waller Health 1 - 1st Flr Room 113 | Add | 355
LX-0698-01-0113A | Waller Health 1 - 1st Flr Room 113A | Add | 122
LX-0698-01-0115 | Waller Health 1 - 1st Flr Room 115 | Add | 735
LX-0698-01-0116 | Waller Health 1 - 1st Flr Room 116 | Add | 783
LX-0698-01-0116A | Waller Health 1 - 1st Flr Room 116A | Add | 121
LX-0698-01-0119 | Waller Health 1 - 1st Flr Room 119 | Add | 736
LX-0698-01-0120 | Waller Health 1 - 1st Flr Room 120 | Add | 239
LX-0698-01-0122 | Waller Health 1 - 1st Flr Room 122 | Add | 34
LX-0698-01-0123 | Waller Health 1 - 1st Flr Room 123 | Add | 358
LX-0698-02-0200A | Waller Health 1 - 2nd Flr Room 200A | Add | 113
LX-0698-02-0201 | Waller Health 1 - 2nd Flr Room 201 | Add | 273
LX-0698-02-0202 | Waller Health 1 - 2nd Flr Room 202 | Add | 317
LX-0698-02-0203 | Waller Health 1 - 2nd Flr Room 203 | Add | 275
LX-0698-02-0204 | Waller Health 1 - 2nd Flr Room 204 | Add | 962
LX-0698-02-0204A | Waller Health 1 - 2nd Flr Room 204A | Add | 108
LX-0698-02-0204B | Waller Health 1 - 2nd Flr Room 204B | Add | 163
LX-0698-02-0204C | Waller Health 1 - 2nd Flr Room 204C | Add | 114
LX-0698-02-0204D | Waller Health 1 - 2nd Flr Room 204D | Add | 121
LX-0698-02-0204E | Waller Health 1 - 2nd Flr Room 204E | Add | 117
LX-0698-02-0204F | Waller Health 1 - 2nd Flr Room 204F | Add | 117
LX-0698-02-0204G | Waller Health 1 - 2nd Flr Room 204G | Add | 109
LX-0698-02-0205 | Waller Health 1 - 2nd Flr Room 205 | Add | 71
LX-0698-02-0207 | Waller Health 1 - 2nd Flr Room 207 | Add | 291
LX-0698-02-0209 | Waller Health 1 - 2nd Flr Room 209 | Add | 1333
LX-0698-02-0209A | Waller Health 1 - 2nd Flr Room 209A | Add | 179
LX-0698-02-0209D | Waller Health 1 - 2nd Flr Room 209D | Add | 117
LX-0698-02-0209E | Waller Health 1 - 2nd Flr Room 209E | Add | 109
LX-0698-02-0212 | Waller Health 1 - 2nd Flr Room 212 | Add | 166
LX-0698-02-0216 | Waller Health 1 - 2nd Flr Room 216 | Add | 1218
LX-0698-02-0216A | Waller Health 1 - 2nd Flr Room 216A | Add | 166
LX-0698-02-0216B | Waller Health 1 - 2nd Flr Room 216B | Add | 113
LX-0698-02-0216C | Waller Health 1 - 2nd Flr Room 216C | Add | 101
LX-0698-02-0219 | Waller Health 1 - 2nd Flr Room 219 | Add | 112
LX-0698-02-0219A | Waller Health 1 - 2nd Flr Room 219A | Add | 112
LX-0698-02-0219B | Waller Health 1 - 2nd Flr Room 219B | Add | 120
LX-0698-02-0219C | Waller Health 1 - 2nd Flr Room 219C | Add | 120
LX-0698-02-0219D | Waller Health 1 - 2nd Flr Room 219D | Add | 126
LX-0698-02-0219E | Waller Health 1 - 2nd Flr Room 219E | Add | 127
LX-0698-02-0219F | Waller Health 1 - 2nd Flr Room 219F | Add | 125
LX-0698-02-0219G | Waller Health 1 - 2nd Flr Room 219G | Add | 355
LX-0698-02-0220 | Waller Health 1 - 2nd Flr Room 220 | Add | 101
LX-0698-02-0222 | Waller Health 1 - 2nd Flr Room 222 | Add | 34
LX-0698-03-0300A | Waller Health 1 - 3rd Flr Room 300A | Add | 113
LX-0698-03-0301 | Waller Health 1 - 3rd Flr Room 301 | Add | 273
LX-0698-03-0302 | Waller Health 1 - 3rd Flr Room 302 | Add | 317
LX-0698-03-0303 | Waller Health 1 - 3rd Flr Room 303 | Add | 275
LX-0698-03-0304 | Waller Health 1 - 3rd Flr Room 304 | Add | 151
LX-0698-03-0304A | Waller Health 1 - 3rd Flr Room 304A | Add | 197
LX-0698-03-0304B | Waller Health 1 - 3rd Flr Room 304B | Add | 125
LX-0698-03-0304C | Waller Health 1 - 3rd Flr Room 304C | Add | 127
LX-0698-03-0304D | Waller Health 1 - 3rd Flr Room 304D | Add | 114
LX-0698-03-0305 | Waller Health 1 - 3rd Flr Room 305 | Add | 71
LX-0698-03-0306 | Waller Health 1 - 3rd Flr Room 306 | Add | 115
LX-0698-03-0307 | Waller Health 1 - 3rd Flr Room 307 | Add | 291
LX-0698-03-0308 | Waller Health 1 - 3rd Flr Room 308 | Add | 726
LX-0698-03-0308A | Waller Health 1 - 3rd Flr Room 308A | Add | 122
LX-0698-03-0308B | Waller Health 1 - 3rd Flr Room 308B | Add | 134
LX-0698-03-0309A | Waller Health 1 - 3rd Flr Room 309A | Add | 125
LX-0698-03-0309B | Waller Health 1 - 3rd Flr Room 309B | Add | 126
LX-0698-03-0309C | Waller Health 1 - 3rd Flr Room 309C | Add | 125
LX-0698-03-0316 | Waller Health 1 - 3rd Flr Room 316 | Add | 1107
LX-0698-03-0316A | Waller Health 1 - 3rd Flr Room 316A | Add | 134
LX-0698-03-0316B | Waller Health 1 - 3rd Flr Room 316B | Add | 122
LX-0698-03-0316C | Waller Health 1 - 3rd Flr Room 316C | Add | 114
LX-0698-03-0317 | Waller Health 1 - 3rd Flr Room 317 | Add | 1523
LX-0698-03-0317A | Waller Health 1 - 3rd Flr Room 317A | Add | 125
LX-0698-03-0317B | Waller Health 1 - 3rd Flr Room 317B | Add | 126
LX-0698-03-0317C | Waller Health 1 - 3rd Flr Room 317C | Add | 126
LX-0698-03-0320 | Waller Health 1 - 3rd Flr Room 320 | Add | 275
LX-0698-03-0320A | Waller Health 1 - 3rd Flr Room 320A | Add | 135
LX-0698-03-0321 | Waller Health 1 - 3rd Flr Room 321 | Add | 719
LX-0698-03-0322 | Waller Health 1 - 3rd Flr Room 322 | Add | 34
LX-0698 | Waller Health Care Annex 1 | Change SqFt
LX-0698-00 | Waller Health 1 - Basement | Change SqFt
LX-0698-00-EL0000A | Waller Health 1 - Bsmt Elevator A | Change SqFt
LX-0698-00-ST0000A | Waller Health 1 - Bsmt Stair A | Change SqFt
LX-0698-00-ST0000B | Waller Health 1 - Bsmt Stair B | Change SqFt
LX-0698-01 | Waller Health 1 - 1st Floor | Change SqFt
LX-0698-01-0100 | Waller Health 1 - 1st Flr Room 100 | Change SqFt
LX-0698-01-EL0100A | Waller Health 1 - 1st Flr Elevator A | Change SqFt
LX-0698-01-ST0100A | Waller Health 1 - 1st Flr Stair A | Change SqFt
LX-0698-01-ST0100B | Waller Health 1 - 1st Flr Stair B | Change SqFt
LX-0698-01-XA0101 | Waller Health 1 - Portico | Change SqFt
LX-0698-02 | Waller Health 1 - 2nd Floor | Change SqFt
LX-0698-02-0200 | Waller Health 1 - 2nd Flr Room 200 | Change SqFt
LX-0698-02-EL0200A | Waller Health 1 - 2nd Flr Elevator A | Change SqFt
LX-0698-02-ST0200A | Waller Health 1 - 2nd Flr Stair A | Change SqFt
LX-0698-02-ST0200B | Waller Health 1 - 2nd Flr Stair B | Change SqFt
LX-0698-03 | Waller Health 1 - 3rd Floor | Change SqFt
LX-0698-03-0300 | Waller Health 1 - 3rd Flr Room 300 | Change SqFt
LX-0698-03-EL0300A | Waller Health 1 - 3rd Flr Elevator A | Change SqFt
LX-0698-03-ST0300A | Waller Health 1 - 3rd Flr Stair A | Change SqFt
LX-0698-03-ST0300B | Waller Health 1 - 3rd Flr Stair B | Change SqFt
LX-0698-04 | Waller Health 1 - Roof | Change SqFt

## Lookup
No Change | Yes | Arianna Baird | No Change | Add A Door | Requested | Add
New Tag Required | No | Janet Schwartz | New Sign Required | Add This Room Number | Awaiting Installation | Deactivate
N/A | N/A | Aaron Newell | N/A | Change Door Swing | Installed | Change SqFt
Action Required |  | Gretchen Tucker | Action Required | Changed Roof ID | Removed | Change Description
Remove Old Tag |  | Maureen Dreckman | Remove Old Sign | Delete This Room Number | 0 | Move Equip
|  | Nicole Kline | Move Sign to New Location | Sq ft Correction
|  | Michael Ammerman |  | Moved a Wall And Door
|  | Kevin Dohner |  | New Room ID Added For SAP Purposes
|  | Sawyer Wilson |  | No Change to Room
Door Removed, Door Opening Exists
Remove A Door
Room Label Change: xxx Changed To xxx
Room Created
Room Deleted
Room Made Bigger
Room Made Smaller
Wall And Doorway Removed Between Rm xxx And Rm xxx
Walls Removed
Windows Added

## BuildingList
Building ID | Building Name
0001 | Taylor Education Building
0003 | Research Facility #1
0004 | Central Heating Plant #2
0005 | Frank D. Peterson Service Building
0009 | Patterson Hall
0012 | Blazer Dining
0014 | Hilary J. Boone Center
0015 | William B. Sturgill Development Building
0016 | Gatehouse KY Clinic
0017 | Dickey Hall
0019 | Memorial Coliseum
0020 | Engineering Transportation Research Garage
0021 | Old Engineers Residence
0022 | Fine Arts Guignol Building
0023 | Safety & Security
0024 | Lafferty Hall
0025 | White Hall Classroom Building
0027 | Patterson Office Tower
0028 | Barker Hall
0031 | Frazee Hall
0032 | Main Building
0033 | Ezra Gillis Building
0034 | Carol Martin Gatton Business & Economics Building
0035 | Miller Hall
0038 | Engineering Annex
0039 | Margaret I. King Library
0040 | Maxwell Place
0041 | Pence Hall
0042 | Grehan Journalism Building
0043 | S. J. Sam Whalen Building
0044 | Kastle Hall
0045 | McVey Hall
0046 | Anderson Hall Tower
0047 | C. W. Mathews Building
0048 | Law Building
0049 | Memorial Hall
0050 | Erikson Hall
0051 | Mineral Industries Building
0052 | Terrell Civil Engineering Building
0053 | Slone Research Building
0054 | Funkhouser Building
0055 | Chemistry-Physics Building
0056 | Breckinridge Hall
0057 | Kinkead Hall
0058 | Bradley Hall
0059 | Bowman Hall
0061 | Tobacco Research Laboratory
0064 | Scovell Hall
0065 | Small Animal Lab
0066 | Agronomy Head House
0067 | Chi Omega Sorority
0068 | Delta Delta Delta Sorority
0069 | Alpha Delta Pi Sorority
0073 | Thomas Poe Cooper Building
0074 | Shively Track & Field Stadium
0075 | Kelley Hall
0076 | Dimock Animal Pathology
0077 | 653 Maxwelton Ct
0078 | Med Center Annex #5
0079 | Herman Lee Donovan Hall
0080 | Lyman T. Johnson Hall
0081 | Cooker Trailer Storage
0082 | Multi-Disciplinary Science Building (MDS)
0084 | Gatehouse Roach Bldg
0085 | Medical Center Heating and Cooling Plant
0086 | Medical Behavioral Science Building
0087 | Medical Center Storage Facility
0088 | Agriculture Motor Pool
0089 | Cooling Plant #1
0090 | Art and Visual Studies Building
0091 | Agriculture Science Center North
0092 | Seed House
0093 | Ben F. Roach Cancer Care Facility
0094 | Cooper House
0095 | Frances Jewell Hall
0096 | Dorothy Enslow Combs Cancer Research Building
0097 | E. S. Good Barn
0098 | Marylou Whitney and John Hendrickson Cancer Facility for Women
0099 | Gluck Equine Research Building
0100 | Haggin Hall
0101 | Reynolds Warehouse #1
0102 | Reynolds Warehouse #2
0104 | Chellgren Hall
0107 | Mining & Minerals Resources Building
0108 | Center for Robotics & Manufacturing Systems
0109 | Wendell & Vickie Bell Soccer Complex
0110 | Maintenance Building (Athletics)
0113 | Shively Sports Center
0117 | Soccer Filming Tower
0119 | Helen King Alumni Building
0120 | Woodland Glen II
0121 | Sigma Nu Fraternity
0122 | Delta Gamma Sorority
0123 | Georgia M. Blazer Hall
0124 | Delta Zeta Sorority
0125 | Kappa Alpha Theta Sorority
0126 | Phi Sigma Kappa Fraternity
0127 | Alpha Gamma Delta Sorority
0128 | Kappa Delta Sorority
0129 | Delta Sigma Phi Fraternity
0139 | The 90
0141 | New Farmhouse Fraternity
0143 | Blanding II
0144 | Blanding III
0145 | Blanding Tower
0146 | Blanding IV
0147 | Complex Commons
0148 | Kirwan IV
0149 | Kirwan Tower
0150 | Kirwan III
0151 | Kirwan II
0152 | Kirwan I
0153 | Blanding I
0154 | Head House
0155 | Greenhouse No 2
0156 | Greenhouse No 4
0157 | Greenhouse No 7
0158 | Greenhouse No 5
0159 | Greenhouse No 3
0160 | Greenhouse No 1
0161 | Greenhouse No 9
0162 | Greenhouse No 11
0163 | Greenhouse No 6
0164 | Greenhouse No 12
0166 | Gatehouse Administration Dr
0167 | Gatehouse Rose & Chem/Physics
0172 | Alpha Gamma Rho Fraternity
0173 | Gatehouse Med Plaza
0174 | Don & Cathy Jacobs Science Building
0175 | Gatehouse Med Plaza
0176 | Gatehouse KY Clinic
0178 | Gatehouse Young Library
0181 | Woodland Glen III
0183 | Isolation Barn
0184 | Agricultural Machine Research Lab
0186 | Woodland Glen IV
0188 | Woodland Glen V
0189 | Shawneetown Bldg A
0190 | Shawneetown Bldg B
0191 | Shawneetown Bldg D
0192 | Shawneetown Bldg F
0193 | Shawneetown Bldg E
0194 | Shawneetown Bldg C
0196 | Band Viewing Tower
0197 | Parking Garage No 1
0198 | Parking Garage No 2
0199 | Parking Garage No 3
0200 | Wethington Allied Health Building
0202 | Parking Garage No 5
0204 | Cooling Plant #2
0205 | Phi Mu
0207 | Arts Metal Building
0210 | Reynolds Warehouse #4
0211 | Maxwell Place Garage
0212 | Lancaster Aquatics
0213 | Boone Tennis Center
0214 | Flammable Storage Building
0215 | W. P. Garrigus Building
0216 | Multi-Disciplinary Research Lab #3
0217 | Electric Substation #2
0219 | Seaton Center
0220 | Bernard Johnson Student Rec Ctr
0222 | Kroger Field
0223 | Warren Wright Medical Plaza
0224 | Lucille Caudill Little Fine Arts Library
0225 | T H Morgan Biological Sciences
0227 | Recreation Equipment Storage Building
0229 | Agricultural Distribution Center
0230 | Sanders-Brown Center on Aging
0232 | College of Nursing
0235 | John W Oswald Building
0236 | Kentucky Tobacco Research and Development Center
0241 | Singletary Center for the Arts
0243 | Greg Page Apartments 1
0244 | Greg Page Apartments 2
0245 | Greg Page Apartments 3
0246 | Greg Page Apartments 4
0247 | Greg Page Apartments 5
0248 | Greg Page Apartments 6
0249 | Greg Page Apartments 7
0250 | Greg Page Apartments 8
0252 | Greg Page Apartments 10
0253 | Greg Page Apartments 11
0254 | Greg Page Apartments 12
0255 | Greg Page Apartments 13
0256 | Greg Page Apartments 14
0257 | Greg Page Apartments 15
0258 | Greg Page Apartments 16
0259 | Greg Page Apartments 17
0260 | Greg Page Apartments 18
0261 | Greg Page Apartments 19
0262 | Greg Page Apartments 20
0263 | Greg Page Apartments 21
0264 | Greg Page Apartments 22
0265 | Greg Page Apartments 23
0266 | Greg Page Apartments 24
0267 | Greg Page Apartments 25
0268 | Greg Page Food Storage Laundry
0269 | Communications Building
0274 | Moloney Building
0275 | Bruce Poundstone Regulatory Services Building
0276 | Charles E. Barnhart Building
0277 | EJ Nutter Training Center
0278 | PPD Storage Building
0279 | BIRP Building
0280 | Joe Craft Football Training Facility
0281 | Oliver H. Raymond Civil Engineering
0282 | Gas Storage Building
0283 | Hagan Baseball Stadium
0284 | Kentucky Clinic
0285 | Nutter Field House
0286 | ASTeCC
0288 | PPD Greenhouse
0289 | Stadium View Storage Building
0293 | UK Hospital - Chandler Medical Center & Hospital
0294 | Gill Heart and Vascular Institute
0297 | Dental Science Building
0298 | William R. Willard Medical Education Building
0300 | Arboretum Tool Shed
0301 | 154 Bonnie Brae
0302 | Dorotha Smith Oatts Visitor Center
0303 | Arboretum Restrooms
0305 | Peter P. Bosomworth Health Sciences Research Building
0308 | Hospital Smoking Shelter
0312 | Plant Sciences
0314 | 252 East Maxwell St
0315 | 206 East Maxwell St
0333 | 641 South Limestone St
0336 | Thomas D Clark Building
0343 | Bingham Davis House
0344 | Raymond F. Betts House
0345 | Max Kade German House and Cultural Center
0346 | 654 Maxwelton Ct
0347 | 624 Maxwelton Ct
0348 | 626 Maxwelton Ct
0349 | 641 Maxwelton Ct
0350 | 643 Maxwelton Ct
0351 | 644 Maxwelton Ct
0353 | 520 Oldham Ct
0377 | 319 Rose Lane
0378 | 321 Rose Lane
0382 | Sky Blue Solar House
0391 | Bus Shelter #2
0393 | Bus Shelter #7
0394 | Bus Shelter #6
0397 | Bus Shelter #9
0398 | Bus Shelter #10
0399 | Bus Shelter #11
0400 | Ellen H. Richards House
0401 | Weldon House
0403 | Weldon House Unit 2
0413 | Softball/Soccer Locker Rooms
0417 | 660 South Limestone
0419 | Bus Shelter #13
0420 | 424 Euclid Avenue
0432 | Commonwealth House
0433 | William E and Casiana Schmidt Vocal Arts Center
0442 | Ligon House
0446 | John Cropp Softball Stadium
0447 | Hitting Pavilion
0448 | Football Storage Shed
0449 | Shively Grounds Storage Building
0453 | Shively Grounds Building
0456 | W.T. Young Library
0462 | Sarah Bennett Holmes Hall
0463 | Cleona Belle Matthews Boyd Hall
0465 | Pavilion at Kroger Field
0473 | 505 Oldham Ct
0481 | LCC Academic Tech Building
0484 | Real Properties Garage
0485 | Boone Tennis Stadium
0487 | 518 Oldham Ct
0488 | Woodland Early Learning Center
0489 | 1117 South Limestone
0490 | Environmental Quality Management
0494 | Stuckert Career Center
0495 | James F. Hardymon Communications Building
0503 | Ralph G Anderson Building (Mech Eng)
0504 | Phi Gamma Delta Fraternity (FIJI)
0505 | Kappa Sigma Fraternity
0507 | Sigma Alpha Epsilon Fraternity
0509 | Biomedical Biological Sciences Research Building
0514 | Central Utility Plant #4
0517 | College of Medicine Learning Center
0518 | BBSRB Generator Building
0564 | 630 South Broadway
0565 | John T. Smith Hall
0566 | Dale E. Baldwin Hall
0567 | Margaret Ingels Hall
0568 | David P. Roselle Hall
0571 | Parking Structure #6
0572 | Parking Structure #7
0582 | University Health Service
0585 | Baseball Training Pavilion
0592 | Storage Shed
0596 | Lee T. Todd, Jr. Building
0601 | Parking Structure #8
0602 | Pavilion A
0604 | Joe Craft Center
0611 | Medical Office Building (Samaritan)
0612 | Samaritan Chiller Building
0613 | Samaritan Parking Structure
0616 | Seaton Center Storage
0618 | MacAdam Student Observatory
0626 | 1119 S. Limestone
0633 | Davis Marksbury Building
0644 | Wildcat Coal Lodge
0651 | Mandrell Hall
0652 | Bosworth Hall
0653 | Sanders Hall
0654 | Building 100
0655 | Building 200
0656 | Building 300
0657 | Building 400
0658 | Maintenance Bldg.
0659 | Gas Building
0660 | Maxwelton Ct. Apts #1
0661 | Maxwelton Ct. Apts #2
0662 | Maxwelton Ct. Apts #3
0663 | Maxwelton Ct. Apts #4
0664 | Maxwelton Ct. Apts #5
0665 | Maxwelton Ct. Apts #6
0666 | Maxwelton Ct. Apts #7
0667 | Maxwelton Ct. Apts #8
0668 | Maxwelton Ct. Apts #9
0669 | Maxwelton Ct. Apts #10
0670 | Maxwelton Ct. Apts #11
0671 | Maxwelton Ct. Apts #12
0672 | Maxwelton Ct. Apts #13
0673 | Maxwelton Ct. Apts #14
0674 | Maxwelton Ct. Apts #15
0675 | Maxwelton Ct. Apts #16
0676 | Bill Gatton Student Center
0677 | University Flats
0678 | Lewis Hall
0679 | Healthy Kentucky Research Building
0682 | Kentucky Proud Park
0690 | 441 Rose Ln
0695 | Blue Lot Bus Shelter
0698 | University Inn #1
0699 | University Inn #2
0702 | Soccer Support Building
0703 | Senior Center
0708 | Kiln Enclosure Building
0711 | Orange Lot Bus Shelter
0712 | 430 Transylvania Park
0713 | 463 Rose Ln
0715 | 600 S Broadway
0717 | 156 Leader Ave
0718 | 125 State St
1200 | Electric Substation #1
1201 | Electric Substation #3
2100 | Alpha Chi Omega Sorority
2101 | Beta Theta Pi Fraternity
2102 | New Kappa Alpha Theta Sorority
2103 | Phi Kappa Tau
8633 | UK HealthCare Good Samaritan Hospital
9127 | 1101 S. Limestone
9766 | New Equine Analytical Chemistry Lab
9772 | 1221 S. Broadway
9813 | Child Development Center of the Bluegrass, Inc.
9853 | Shriners Hospitals for Children Medical Center - Lexington
9854 | Anthropology Research Building
9861 | 845 Angliana Ave
9873 | UKHC Midwife Clinic
9875 | Vaughan Warehouse and Office
9876 | Vaughan Warehouse #1
9877 | Vaughan Warehouse #2
9878 | Vaughan Warehouse #7
9879 | Vaughan Warehouse #3
9881 | Vaughan Warehouse #4
9882 | Vaughan Warehouse #5
9925 | Alpha Phi Sorority
9983 | College of Medicine Building
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A
0 | #N/A