## KD Changes
Building ID | 8633 |  |  |  | Status Date: | 2015-04-29 |  |  | # of Rooms Waiting for eBARS Tags | # of Rooms Waiting for Door Signs |  |  |  | Verified By: | Date:
Name | UK HealthCare Good Samaritan Hospital |  |  |  | CAD Operator | Adam Davidson |  |  | 1 | 0
Room ID | Floor | Description of Change | Change to SqFt | Old SqFt | New SqFt | eBARS Tag Status | Door Signage | Comments | eBARS Tag Progress | Date | Issues | New Sign Progress | Date | Issues
B-450 | 04 | Casework removed | Yes | 586 | 459 | No Change | N/A | New cabinets and work station installed. | N/A |  |  | N/A
B-450B | 04 | Room Created | Yes | 0 | 127 | New Tag Required | N/A | New Door and wall Installed. New cabinets installed.
B-550 | 05 | CaseWork removed | No |  |  | No Change | N/A | New Work station installed
B-550A |  | Door and wall removed, casework removed | Yes | 152 | 153 | No Change | N/A | New cabinets and work station installed
B-550B | 05 | Door and wall removed, New door installed | No |  |  | No Change | N/A | New cabinets and work station installed | N/A |  |  | N/A
B-650 | 06 | CaseWork removed | No |  |  | No Change | N/A | New Work station installed
B-650A | 06 | CaseWork removed | No |  |  | No Change |  | New cabinets and work station installed
B-650B | 06 | CaseWork removed, New door installed | No |  |  | No Change | N/A | New cabinets and work station installed | N/A |  |  | N/A
[6 empty] | Total Tags Required | Total Signs Required |  | Total Tags Installed |  |  | Total Signs Installed
[6 empty] | 1 | 0 |  | 0 |  |  | 0
End of Data Validation

## SAP Changes
Building ID | 8633 |  | Status Date: | 2015-04-29
Name | UK HealthCare Good Samaritan Hospital |  | CAD Operator | Adam Davidson
SAP Functional Location | Room Description | Action | SqFt | Comments
LX-8633-04-B450B | SAMARITAN HOSPITAL - Room B450B | Add | 127
End of Data Validation

## Lookup
No Change | Yes | Adam Davidson | No Change | Add A Door | Requested | Add
New Tag Required | No | Janet Schwartz | New Sign Required | Add This Room Number | Awaiting Installation | Inactivate
N/A | N/A | Barry Richardson | N/A | Change Door Swing | Installed | Change SqFt
Action Required |  | Laura Greenfield | Action Required | Delete This Room Number | Removed | Change Description
Remove Old Tag |  | Chris Curtis | Remove Old Sign | Gross | 0
|  | Gretchen Tucker | Move Sign to New Location | Moved a Wall And Door
New Room Added For SAP Purposes
No Change to Room
Door Removed, Door Opening Exists
Remove A Door
Room Label Change: xxx Changed To xxx
Room Created
Room Deleted
Room Made Bigger
Room Made Smaller
Wall And Doorway Removed Between Rm xxx And Rm xxx
Walls Removed
Windows Added

## BuildingList
Building ID | Building Name
0001 | Taylor Education Building
0002 | Scott Street Building
0003 | Research Facility #1
0004 | Central Heating Plant #2
0005 | Frank D. Peterson Service Building
0009 | Patterson Hall
0012 | Blazer Hall
0014 | Boone Faculty Center
0015 | William B. Sturgill Development Building
0016 | Gatehouse KY Clinic
0017 | Dickey Hall
0019 | Memorial Coliseum
0020 | Engineering Transportation Research Garage
0021 | Old Engineers Residence
0022 | Fine Arts Guignol Building
0023 | Safety & Security
0024 | Lafferty Hall
0025 | White Hall Classroom Building
0026 | Student Center Addition
0027 | Patterson Office Tower
0028 | Barker Hall
0029 | Alumni Gym
0030 | Student Center
0031 | Frazee Hall
0032 | Main Building
0033 | Ezra Gillis Building
0034 | Carol Martin Gatton Business & Economics Building
0035 | Miller Hall
0036 | Gatehouse Gate 2
0037 | 109 State St
0038 | Engineering Annex
0039 | Margaret I. King Library
0040 | Maxwell Place
0041 | Pence Hall
0042 | Grehan Journalism Building
0043 | S. J. Sam Whalen Building
0044 | Kastle Hall
0045 | McVey Hall
0046 | Anderson Hall Tower
0047 | C. W. Mathews Building
0048 | Law Building
0049 | Memorial Hall
0050 | Erikson Hall
0051 | Mineral Industries Building
0052 | Terrell Civil Engineering Building
0053 | Slone Research Building
0054 | Funkhouser Building
0055 | Chemistry-Physics Building
0056 | Breckinridge Hall
0057 | Kinkead Hall
0058 | Bradley Hall
0059 | Bowman Hall
0061 | Tobacco Research Laboratory
0064 | Scovell Hall
0065 | Small Animal Lab
0066 | Agronomy Head House and Greenhouses 1 & 2
0067 | Chi Omega Sorority
0068 | Delta Delta Delta Sorority
0069 | Alpha Delta Pi Sorority
0073 | Thomas Poe Cooper Building
0074 | Shively Track & Field Stadium
0075 | Kelley Hall
0076 | Dimock Animal Pathology
0077 | 653 Maxwelton Ct
0078 | Med Center Annex #5
0079 | Central Hall II
0080 | Central Hall I
0081 | Cooker Trailer Storage
0082 | Multi-Disciplinary Science Building (MDS)
0083 | 453 Columbia
0084 | Gatehouse Roach Bldg
0085 | Medical Center Heating and Cooling Plant
0086 | Medical Behavioral Science Building
0087 | Medical Center Storage Facility
0088 | Agriculture Motor Pool
0089 | Cooling Plant #1
0090 | University Lofts
0091 | Agriculture Science Center North
0092 | Seed House
0093 | Ben F. Roach Cancer Care Facility
0094 | Cooper House
0095 | Champions Court I
0096 | Dorothy Enslow Combs Cancer Research Building
0097 | E. S. Good Barn
0098 | Marylou Whitney and John Hendrickson Cancer Facility for Women
0099 | Gluck Equine Research Building
0100 | Haggin Hall
0101 | Reynolds Warehouse #1
0102 | Reynolds Warehouse #2
0103 | Reynolds Warehouse #3
0104 | Woodland Glen I
0105 | Commonwealth Village #2
0106 | Commonwealth Village #1
0107 | Mining & Minerals Resources Building
0108 | Center for Robotics & Manufacturing Systems
0109 | Wendell & Vickie Bell Soccer Complex
0110 | Maintenance Building (Athletics)
0113 | Shively Sports Center
0117 | Soccer Filming Tower
0119 | Helen King Alumni Building
0120 | Woodland Glen II
0121 | Sigma Nu Fraternity
0122 | Delta Gamma Sorority
0123 | Champions Court II
0124 | Delta Zeta Sorority
0125 | Kappa Alpha Theta Sorority
0126 | Phi Sigma Kappa Fraternity
0127 | Alpha Gamma Delta Sorority
0128 | Kappa Delta Sorority
0129 | Delta Sigma Phi Fraternity
0137 | Alpha Gamma Rho Fraternity
0139 | The 90
0141 | New Farmhouse Fraternity
0143 | Blanding II
0144 | Blanding III
0145 | Blanding Tower
0146 | Blanding IV
0147 | Complex Commons
0148 | Kirwan IV
0149 | Kirwan Tower
0150 | Kirwan III
0151 | Kirwan II
0152 | Kirwan I
0153 | Blanding I
0154 | Head House
0155 | Greenhouse No 2
0156 | Greenhouse No 4
0157 | Greenhouse No 7
0158 | Greenhouse No 5
0159 | Greenhouse No 3
0160 | Greenhouse No 1
0161 | Greenhouse No 9
0162 | Greenhouse No 11
0163 | Greenhouse No 6
0164 | Greenhouse No 12
0165 | 106 Conn Terrace
0166 | Gatehouse Administration Dr
0167 | Gatehouse Rose & Chem/Physics
0170 | Gatehouse Student Center
0172 | Alpha Gamma Rho Fraternity
0173 | Gatehouse Med Plaza
0174 | Academic Science Building
0175 | Gatehouse Med Plaza
0176 | Gatehouse KY Clinic
0177 | Residence Motor Pool
0178 | Gatehouse Young Library
0179 | Temporary Bookstore
0180 | 113 State St
0181 | Woodland Glen III
0182 | Isolation Barn Incinerator
0183 | Isolation Barn
0184 | Agricultural Machine Research Lab
0185 | Garage by Motor Pool Residence
0186 | Woodland Glen IV
0187 | Bus Shelter #5
0188 | Woodland Glen V
0189 | Shawneetown Bldg A
0190 | Shawneetown Bldg B
0191 | Shawneetown Bldg D
0192 | Shawneetown Bldg F
0193 | Shawneetown Bldg E
0194 | Shawneetown Bldg C
0196 | Stoll Field Viewing Tower
0197 | Parking Garage No 1
0198 | Parking Garage No 2
0199 | Parking Garage No 3
0200 | Wethington Allied Health Building
0202 | Parking Garage No 5
0203 | 1037 S. Limestone
0204 | Cooling Plant #2
0205 | Phi Mu
0207 | Arts Metal Building
0210 | Reynolds Warehouse #4
0211 | Maxwell Place Garage
0212 | Lancaster Aquatics
0213 | Boone Tennis Center
0214 | Flammable Storage Building
0215 | W. P. Garrigus Building
0216 | Multi-Disciplinary Research Lab #3
0217 | Electric Substation #2
0219 | Seaton Center
0220 | Bernard Johnson Student Rec Ctr
0222 | Commonwealth Stadium
0223 | Warren Wright Medical Plaza
0224 | Lucille Caudill Little Fine Arts Library
0225 | T H Morgan Biological Sciences
0227 | Recreation Equipment Storage Building
0229 | Agricultural Distribution Center
0230 | Sanders-Brown Center on Aging
0231 | Farm Maintenance Storage Shed
0232 | College of Nursing
0235 | John W Oswald Building
0236 | Kentucky Tobacco Research and Development Center
0241 | Singletary Center for the Arts
0243 | Greg Page Apartments 1
0244 | Greg Page Apartments 2
0245 | Greg Page Apartments 3
0246 | Greg Page Apartments 4
0247 | Greg Page Apartments 5
0248 | Greg Page Apartments 6
0249 | Greg Page Apartments 7
0250 | Greg Page Apartments 8
0252 | Greg Page Apartments 10
0253 | Greg Page Apartments 11
0254 | Greg Page Apartments 12
0255 | Greg Page Apartments 13
0256 | Greg Page Apartments 14
0257 | Greg Page Apartments 15
0258 | Greg Page Apartments 16
0259 | Greg Page Apartments 17
0260 | Greg Page Apartments 18
0261 | Greg Page Apartments 19
0262 | Greg Page Apartments 20
0263 | Greg Page Apartments 21
0264 | Greg Page Apartments 22
0265 | Greg Page Apartments 23
0266 | Greg Page Apartments 24
0267 | Greg Page Apartments 25
0268 | Greg Page Food Storage Laundry
0269 | Communications Building
0272 | Information Building
0274 | Moloney Building
0275 | Bruce Poundstone Regulatory Services Building
0276 | Charles E. Barnhart Building
0277 | Nutter Football Training Facility
0278 | PPD Storage Building
0279 | BIRP Building
0280 | The Football Training Facility
0281 | Oliver H. Raymond Civil Engineering
0282 | Gas Storage Building
0283 | Hagan Baseball Stadium
0284 | Kentucky Clinic
0285 | Nutter Field House
0286 | ASTeCC
0287 | Electric HVAC Building
0288 | PPD Greenhouse
0289 | Hazardous Waste Storage
0293 | UK Hospital - Chandler Medical Center & Hospital
0294 | Gill Heart Institute
0297 | Dental Science Building
0298 | William R. Willard Medical Education Building
0300 | Arboretum Tool Shed
0301 | 154 Bonnie Brae
0302 | Dorotha Smith Oatts Visitor Center
0303 | Arboretum Restrooms
0305 | Peter P. Bosomworth Health Sciences Research Building
0312 | Plant Sciences
0313 | 455 Woodland Ave
0314 | 252 East Maxwell St
0315 | 206 East Maxwell St
0317 | 408 Pennsylvania Ct
0324 | 315 Scott St
0325 | 317 Scott St
0327 | 321 Scott St
0333 | 641 South Limestone St
0336 | Thomas D Clark Building
0337 | 663 South Limestone Garage
0343 | Bingham Davis House
0344 | Raymond F. Betts House
0345 | Max Kade German House and Cultural Center
0346 | 654 Maxwelton Ct
0347 | 624 Maxwelton Ct
0348 | 626 Maxwelton Ct
0349 | 641 Maxwelton Ct
0350 | 643 Maxwelton Ct
0351 | 644 Maxwelton Ct
0353 | 520 Oldham Ct
0355 | 123 State St
0356 | 119 State St
0360 | 400 Pennsylvania Ct
0361 | 402 Pennsylvania Ct
0362 | 405 Pennsylvania Ct
0363 | 406 Pennsylvania Ct
0365 | 410 Pennsylvania Ct
0377 | 319 Rose Lane
0378 | 321 Rose Lane
0381 | 162-164 Gazette Avenue
0382 | Sky Blue Solar House
0386 | 150 Gazette Avenue
0390 | Bus Shelter #1
0391 | Bus Shelter #2
0392 | Bus Shelter #3
0393 | Bus Shelter #7
0394 | Bus Shelter #6
0397 | Bus Shelter #9
0398 | Bus Shelter #10
0399 | Bus Shelter #11
0400 | Ellen H. Richards House
0401 | Weldon House
0409 | 341-343 Scott St
0412 | 403 Pennsylvania Ct
0413 | Softball/Soccer Locker Rooms
0416 | Bus Shelter #12
0417 | 660 South Limestone
0419 | Bus Shelter #13
0420 | 424 Euclid Avenue
0427 | Bowman's Den
0432 | Commonwealth House
0433 | William E and Casiana Schmidt Vocal Arts Center
0442 | Ligon House
0446 | John Cropp Softball Stadium
0447 | Hitting Pavilion
0448 | Football Storage Shed
0449 | Shively Grounds Storage Building
0453 | Shively Grounds Building
0456 | W.T. Young Library
0460 | 149 Transcript Ave
0461 | 153 Transcript Ave
0462 | Limestone Park I
0463 | Limestone Park II
0465 | Pavilion at Commonwealth Stadium
0467 | 220 Transcript Ave
0473 | 505 Oldham Ct
0481 | LCC Academic Tech Building
0482 | 408 Linden Walk
0484 | Real Properties Garage
0485 | Boone Tennis Stadium
0487 | 518 Oldham Ct
0488 | Woodland Early Learning Center
0489 | 1117 South Limestone
0490 | Environmental Quality Management
0494 | Stuckert Career Center
0495 | James F. Hardymon Communications Building
0503 | Ralph G Anderson Building (Mech Eng)
0504 | Sigma Chi Fraternity House
0505 | Alpha Tau Omega Fraternity
0507 | Sigma Alpha Epsilon Fraternity
0509 | Biomedical Biological Sciences Research Building
0514 | Central Utility Plant #4
0517 | College of Medicine Learning Center
0518 | BBSRB Generator Building
0564 | 630 South Broadway
0565 | John T. Smith Hall
0566 | Dale E. Baldwin Hall
0567 | Margaret Ingels Hall
0568 | David P. Roselle Hall
0571 | Parking Structure #6
0572 | Parking Structure #7
0582 | University Health Service
0585 | Baseball Training Pavilion
0592 | Storage Shed
0596 | Bio-Pharm (BP)
0600 | 413 Pennsylvania Ct
0601 | Parking Structure #8
0602 | Pavilion A
0604 | Joe Craft Center
0607 | 788 Press Avenue
0608 | 792 Press Avenue
0609 | 796 Press Avenue
0610 | 800 Press Avenue
0611 | Medical Office Building (Samaritan)
0612 | Samaritan Chiller Building
0613 | Samaritan Parking Structure
0616 | Seaton Center Storage
0617 | 118 Conn Terrace
0618 | MacAdam Student Observatory
0619 | 102 Conn Terrace
0621 | 104 Conn Terrace
0622 | 108 Conn Terrace
0623 | 110 Conn Terrace
0624 | 120 Conn Terrace
0625 | 1105 S. Limestone
0626 | 1119 S. Limestone
0630 | Air Medical Crew Quarters
0633 | Davis Marksbury Building
0636 | 411 Pennsylvania Court
0637 | 1041 S. Limestone St.
0639 | 1045 S. Limestone St
0641 | 409 Pennsylvania Ct
0644 | Wildcat Coal Lodge
0645 | 179 Leader Ave
0646 | 404 Pennsylvania Ct
0647 | 213 Transcript Ave
0648 | 221 Transcript Ave
0649 | 217 Transcript Ave
0651 | Mandrell Hall
0652 | Bosworth Hall
0653 | Sanders Hall
0654 | Building 100
0655 | Building 200
0656 | Building 300
0657 | Building 400
0658 | Maintenance Bldg.
0659 | Gas Building
0660 | Maxwelton Ct. Apts #1
0661 | Maxwelton Ct. Apts #2
0662 | Maxwelton Ct. Apts #3
0663 | Maxwelton Ct. Apts #4
0664 | Maxwelton Ct. Apts #5
0665 | Maxwelton Ct. Apts #6
0666 | Maxwelton Ct. Apts #7
0667 | Maxwelton Ct. Apts #8
0668 | Maxwelton Ct. Apts #9
0669 | Maxwelton Ct. Apts #10
0670 | Maxwelton Ct. Apts #11
0671 | Maxwelton Ct. Apts #12
0672 | Maxwelton Ct. Apts #13
0673 | Maxwelton Ct. Apts #14
0674 | Maxwelton Ct. Apts #15
0675 | Maxwelton Ct. Apts #16
1200 | Electric Substation #1
1201 | Electric Substation #3
8633 | UK HealthCare Good Samaritan Hospital
9127 | 1101 S. Limestone
9813 | Child Development Center of the Bluegrass, Inc.
9816 | Royal Lexington
9853 | Shriners Hospitals for Children Medical Center - Lexington
9854 | Anthropology Research Building
9925 | Alpha Phi Sorority
9983 | College of Medicine Building
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0